## Sheet1
Quantitative study | Tasks | Starting date | Date of comlpletion | Responsible person
| Data collection | 04.03.2018 | 22.03.2018 | Parul
| Output received from IT |  | 27.03.2018 | Parul
| Draft ppt. |  | 04.04.2018 | Parul
Qualitative study | Tool development | 03.04.2018 | 09.04.2018 | Tamanna, Basanti, Sufia, Sraboni | 9 | 29 | 7 | 21 | 3 | 27
| Field planning | 03.04.2018 | 09.04.2018 | Tamanna, Basanti, Sufia, Sraboni
| Data collection | 10.04.2018 | 26.04.2018 | Tamanna, Basanti, Sufia, Sraboni
| Content analysis | 22.04.2018 | 13.05.2018 | Tamanna, Basanti, Sufia, Sraboni
| Rewriting analysis | 10.07.2018 | 22.07.2018 | Tamanna, Basanti, Sufia, Sraboni
Quantitative & Qualitative analysis & ppt.
| Packages study | 19.06.2018 | 21.06.2018 | Esha
| Quantitative data checking & analysis |  | 24.06.2018 | Esha
| Draft ppt. |  | 29.06.2018 | Esha
| Qualitative data checking & analysis |  | 09.07.2018 | Esha, Parul
| Rewriting analysis | 10.07.2018 | 23.07.2018 | Tamanna, Basanti, Sufia, Sraboni
| Analysis & Draft ppt. |  | 02.08.2018 | Esha
*FFRP report sharing with Nahid bhai on 18th June, 2018, so started studying ANC & PNC packages after that
*There were gaps in qualitative content analysis and identified later, then rewriting was done by the Sr. monitoring officers later one

## Sheet2
Criteria | Findings from RM Checking
| Passed |  |  | Failed
| Findings from QC Re-checking |  |  | Findings from QC Re-checking | [6 empty] | 36 | 29 | 80.56%
| Not Checked | Passed | Failed | Not Checked | Passed | Failed
≥ 3 income sources | 6 | 15 |  |  |  | 2
Nutritious meals twice a day |  | 6 |  | 1
Use of sanitary latrine | 4 | 13 | 5 | 14 | 2 | 24
Use of safe drinking water |  | 2 |  |  | 1 |  |  | 6 |  | 6
Having ducks/chicken/pigeons |  | 3 |  |  |  | 2 |  |  | 1 | 1 |  |  | 180 | 180
Having kitchen garden/vegetables | 5 | 13 | 1 |  |  | 1 |  | 4 | 14 | 18 |  |  | 138 | 134 | 272
Sustainable home |  | 3 | 1 | 6 |  | 1 |  |  |  | 0 |  |  | 42 | 46
All Mandatory criteria | 9 | 29 | 7 | 21 | 3 | 27 |  |  |  | 0
[8 empty] | 5 |  | 5 |  |  | 70 | 18 | 290
[9 empty] | 6 | 6
[8 empty] | 9 | 21 | 30 |  |  | 173 | 173 | 346
[7 empty] | 39.58% | 30% | [6 empty] | 56
[9 empty] | 2 |  | 88.89%
[8 empty] | 2 | 24
1
2
1
1
[8 empty] | 3 | 27